Memo 4C-3/393

To:	Distribution

From:	M. Lammer

Date:	2000-05-10

Subject: 	CINDA 2000 book: publication schedule

First of all I want to apologize for the late distribution of CINDA 99, which was out of my control: Liam Costello and I had finalized the book and submitted it for publication around June 20 1999. However, in spite of my repeated inquiries and urging from August onwards (after my return from a long vacation) there was silence from the publisher until we finally got the printed copies in October 1999.

CINDA 2000 will again be published as cumulative issue for publications between January 1988 and May/June 2000. As detailed in Memo CP-C/313, we will again produce 900 copies, and a joint distribution with CD-CINDA-2000 is planned.

The proposed publication schedule displayed in the attached APPENDIX is only tentative for the following reason: The IAEA discontinues the production of publications in the format and size of the old CINDA book (same as the conference proceedings and technical report series). All publications will be in the DIN-A4 format. However, I could convince our publisher that it is now too late for any programming changes from our side, if we want to publish the CINDA book at the usual time of the year. I also argued that, in particular, it was not worthwhile to invest a large amount of programming effort for an interim solution, as the new CINDA-2001 format will require major changes anyway. This was accepted: we will produce the book file as usual, and the publishers will blow it up to A4 format.

The attached publication schedule relies on the publisher’s promise that no problems with or delays in the publication are to be expected from their side. however, one never knows ….!

Distribution:

DUNFORD@BNLND2.DNE.BNL.GOV

MCLANE@BNLND2.DNE.BNL.GOV

NORDBORG@NEA.FR

KELLETT@NEA.FR

MANOKHIN@IPPE.RSSI.RU

MAEV@IPPE.RSSI.RU

MAY@OBNINSK.RU

CNDC@MIPSA.CIAE.AC.CN

NDS:

M.WIRTZ@iaea.org

LAMMER

MUIR

PRONYAEV

SCHWERER

ZERKIN

APPENDIX

Tentative publication schedule for CINDA 2000

26 June 2000	final deadline for CINDA entries and information for the introductory and Annex pages to reach NDS

7 July 2000	NDS master file processing completed

21 July 2000	NDS book processing completed (including update of CINDA tables)

28 July 2000	CINDA book master completed

18/25 August 2000	printing and binding completed

September 2000	completion of CD-CINDA-2000, distribution of CINDA 2000 as book and CD